## Sheet1
Week | Day | Task | Status
Week 1 | 1 | Setup environment & project structure | completed.
Week 1 | 2 | Setup PostgreSQL & load dataset
Week 1 | 3 | Load data in Python & basic checks
Week 1 | 4 | EDA: Contract vs Churn analysis
Week 1 | 5 | EDA: Tenure & Payment analysis
Week 1 | 6 | Data cleaning (missing, types)
Week 1 | 7 | Encoding & EDA report creation
Week 2 | 1 | Feature engineering (tenure groups, ratios)
Week 2 | 2 | More feature creation & data prep
Week 2 | 3 | Train/test split
Week 2 | 4 | Train Logistic Regression model
Week 2 | 5 | Train Random Forest model
Week 2 | 6 | Train XGBoost model
Week 2 | 7 | Evaluate models & SHAP explainability
Week 3 | 1 | Define LTV & prepare regression data
Week 3 | 2 | Train LTV model
Week 3 | 3 | Save models
Week 3 | 4 | Setup FastAPI project
Week 3 | 5 | Build churn prediction API
Week 3 | 6 | Build LTV API endpoint
Week 3 | 7 | Test API endpoints
Week 4 | 1 | Connect Superset/Metabase to DB
Week 4 | 2 | Create churn dashboards
Week 4 | 3 | Create LTV dashboards
Week 4 | 4 | Add filters and business views
Week 4 | 5 | Polish dashboards
Week 4 | 6 | Dockerize application
Week 4 | 7 | Final testing & documentation